Appendix A
Master Course Development Timeline

If development deadlines are not met and deliverables become 2 weeks behind schedule, the course development process stops. The ID notifies the Senior ID and Discipline Leader.

| Due Date | Deliverable |
| --- | --- |
| Kickoff Week 1 of quarter | Course development team meeting: SME, ID, Discipline Leader, other team members as needed. SME begin development of Course Map – a plan listing course objectives, weekly objectives, topics/lectures that address each objective, assessment measures for each objective |
| Week 2 of quarter | Course Map |
| Week 3 of quarter | Course Map (if necessary) Week 1 Course Content – Lecture/learning activities/assignments w/titles and directions/assessment items using the Weekly Content Template ID reviews and returns Week 1 content with comments and suggestions as necessary. |
| Week 4 of quarter | Week 2 Course Content |
| Week 5 of quarter | Week 3 Course Content |
| Week 6 of quarter | Week 4 Course Content |
| Week 7 of quarter | Week 5 Course Content Midterm Assessment using required assessment format(s) – If applicable |
| Week 8 of quarter | Week 6 Course Content |
| Week 9 of quarter | Week 7 Course Content |
| Week 10 of quarter | Week 8 and Week 9 Course Content |
| Monday Week 11 of quarter | Week 10 Course Content Week 11 Course Content Final Assessment using required assessment formats Summary/Evaluation/Closing Comments using the Weekly Content Template |